# Status Report: AI Identity

Week of March 30 – April 5, 2026

Author: Jeff  |  Date: April 6, 2026

## Executive Summary

Strong execution week for AI Identity. The v0.2.0 milestone was completed with AI Forensics elevated to a first-class product pillar, the Four Pillars governance framework launched, and industry-specific pages for Healthcare and Finance shipped. The landing page was fully migrated from Vite/React to Next.js (all 17 pages ported) for improved SEO and performance. Shadow agent detection UX received significant polish. The project remains on track for the May 5 Product Hunt launch.

Overall Status: ON TRACK

## Key Metrics

| Metric | Target | Actual | Trend | Status |
| --- | --- | --- | --- | --- |
| Commits this week | 15+ | 37 | ↑ Up | ON TRACK |
| Pages migrated (Next.js) | 17 | 17 | Complete | DONE |
| Sentry unresolved issues | 0 | 1 | Low severity | ON TRACK |
| Blog posts (SEO-ready) | 5 | 5 | Complete | DONE |
| Days to Product Hunt launch | — | 29 | ↓ Counting down | ON TRACK |

## Accomplishments This Period

- AI Forensics elevated to first-class product pillar — new landing page live with Four Pillars governance framework (Provenance, Access, Forensics, Compliance).

- Full Next.js migration completed — scaffolded App Router, ported all 17 pages (home, blog, pricing, how-it-works, SDKs, industry verticals, etc.), dynamic sitemap/robots, cleaned up Vite artifacts.

- Healthcare and Finance industry pages added to Solutions dropdown, expanding vertical market positioning.

- Shadow agent detection UX overhaul — deep-links from shadow agent drawer to Forensics with agent_id and date range, expandable request metadata, actionable flows (Register, Block, Dismiss).

- 5 blog posts expanded to 1,800+ words each for SEO/GEO performance; code splitting and Product schema added to pricing page.

- Automated 90-day inactive user cleanup with test script; audit_log trigger properly disabled during user_id nullification.

- Public changelog page, ROADMAP.md, and sitemap entry shipped for transparency.

- About page with founder story and homepage mission section launched.

- QA smoke test cleanup hardened with retry logic and HTTP status verification.

## In Progress

| Item | Owner | Status | ETA | Notes |
| --- | --- | --- | --- | --- |
| Product Hunt launch prep | Jeff | In Progress | May 5 | Copy drafted, assets in progress |
| Welcome email series | Jeff | Drafted | Apr 14 | 3-email post-signup nurture |
| LinkedIn content campaign | Jeff | Active | Ongoing | Carousel posted, daily engagement |
| EU AI Act compliance guide | Jeff | Planned | Apr 20 | Week 2 content piece |
| Agent purge with retention policy | Jeff | In Progress | Apr 12 | Admin endpoint + dashboard UI |

## Risks and Issues

| Risk / Issue | Impact | Mitigation | Owner |
| --- | --- | --- | --- |
| Sentry: Worker SIGTERM signals (PYTHON-FASTAPI-3) | Low — no user impact, 16 events | Seer rates as super-low actionability. Monitor; likely Render platform restarts. | Jeff |
| Solo founder capacity for May 5 launch | Medium — launch timeline | Prioritize launch-critical items (PH assets, email series, landing page polish). Defer non-critical features. | Jeff |
| SEO indexing lag after Next.js migration | Low — organic traffic | Dynamic sitemap and robots.txt shipped. Monitor GSC for crawl issues this week. | Jeff |

## Decisions Needed

| Decision | Context | Deadline | Recommendation |
| --- | --- | --- | --- |
| Design partner pricing tier | Founder Rate (50% off Pro for 6 months) for first 5-10 customers with case study commitment | Apr 20 | Lock in Founder Rate offer; include in PH launch materials. |
| SOC 2 Type II timing | Architecture ready; need policies, pen test, vendor risk. Estimated $20-50K. | Q2 review | Defer until post-launch revenue validates spend. Revisit after 10+ paying customers. |

## Next Period Priorities (April 6–12)

- Finalize Product Hunt launch assets (hero image, maker comment, first-day strategy).

- Ship agent purge with retention policy (admin endpoint + dashboard button).

- Complete and test welcome email series (3-email post-signup nurture).

- Draft EU AI Act compliance guide content piece.

- Continue LinkedIn engagement campaign and daily posting cadence.

- Monitor Sentry for any new issues post-Next.js migration.